## Meeting Notes
Meeting Date | Notes | Comment
Preliminary | Review papers which reference Thomas' paper | Checked Uni Saarland no test interface
| Check if other similar tools already exist | Found some proprietary/open source, none passed Q1 & Q2 tests sofar
| What is output of libpg_query parser? | JSON or protobuf
| Does libpg_query have deparser? | Yes, but only deparses protobuf (not JSON)
13.10.2022 | Do we need the table schemas as input for decorrelation? (if no alias is used)
| Discuss main steps: 1) Translate SQL to Relational Algebra 2) Translate Relational Algebra Tree to SQL (deparser) 3) Decorrelate Relational Algebra Tree | First do step 1 and 2 in parallel (scope: TPC-H queries) Add decorrelation optimization (basic optimizer, detect depedent joins, decorrelating algorithm) In Future add table schema as input
| Check if postgreSQL to relational algebra converter already exists | didn't find anything
25.10.2022 | Parsing correlated queries into dependent join | Doesn't make sense to introduce dependent join in step 3, because then already decorrelated
| Exist can be translated to dep left join. Can "in" always be translated into exists, then to dep left join? | Alex ask Neumann
| Always treat exists as dep join | dependent join will fall away quickly in optimization?
Group by, order by, having as separate nodes
add step where scan whole query and map attributes to relations (for tpch), needed to detect if subquery is correlated
04.11.2022 | Code review | smart pointer > C pointer Keep code recursive rather than iterative for less complexity
| translate "in" to "exists" + null check | side effect: uncorrelated "in" queries will become correlated
Don't integrate CTEs into the main RA tree, but optimize and keep them separately
08.11.2022 | to decorrelate "in" and "exists", need to transform semi joins to regular joins | sql has no semi join or anti join
22.11.2022 | pull subqueries out into CTE instead of from clause | tpch 21 needs this, why not do it for all
| deparsing exists/in | exists/in predicate needs to stay in selection, with a marker
introduce special join for in subquery, not transformed into exists
in values -> store in predicate, don't transform into subquery
defined desired output for all correlated queries
| keep original queries exactly as were | keep "in list", any subqueries (problems with q11 (need group by attribute) and q19 (location of "in" subqueries)
decorrelating simple exists to uncorrelated in
| Neumann Q2 | needs extra relation in from, only because of "<"/">" (see chapter 4, eliminating D)
29.11.2022 | Decorrelating complex exists to cte/left join/null check | Decorrelated TPCH 21 20x slower on umbra… need to compare performance with postgresql
| Confirm: Sideways information passing is not possible in sql | Instread of tempscan, need to scan table
| What is Tempscan operator in Umbra? | Tempscan differentiates Q2 input to Q2 decorrelated sql
In paper, what is T1= A(D)D?
| PostgreSQL instance with TPCH | Alex help setup
08.12.2022 | Only missing join predicate and decoupling in Neumann algo | Neumann algo, how get predicate in first step?
Confirm: When decoupling, Neumanns selection is not necessary
Q2 needs select distinct, due to non-equi predicates
| PostgreSQL performance discussion | careful when transforming exists/in
First focus on Neumann's algo, then consider exists/in discussion
Idea for potential DBIMP project
Sideway information passing
13.12.2022 | Decoupling and sideway information passing (to CTE) done for Q1/Q2 | add support for TPCH (Q2,17,20)
sideways information passing to CTE now only supported if attribute names are unique in CTE (with schema, easier to fix this)
| Neumann paper Q2 predicate is wrong | compare with umbra tree
| When is deadline?/What to prioritise? | unnesting 100% (multiple correlations,all subquery operators, ...)
add schema
clean up code (c-style pointers, error handling)
build UI
visualize RA tree
| Umbra decoupling not optimized in cases… | if "or" a predicate?
if +1 an equi correlated predicate?
20.12.2022 | Q1/Q2 & TPCH decorrelated (special handling for exists/in)
Refactored to smart pointers
| Tests to 100% algorithm | outer/semi joins
multiple correlations in query
set operations (add to sql parser)
| Q1 läuft in Umbra nicht (siehe screenshots) | mit CTEs geht's schon
MA

## Tests
Query | transformation | original | decorrelated | comment
Q1 | subquery with equi predicate -> from subquery with group by
Q2 | subquery with complex predicate -> from subquery with group by |  |  | can also be used by exists/in with complex predicate?
2 | subquery with equi predicate -> from subquery with group by | 226,738 ms | 147,444 ms
4 | exists -> in | 183,439 ms | 186,085 ms | https://mariadb.com/kb/en/exists-to-in-optimization/
17 | subquery with equi predicate -> from subquery with group by | 2412726,898 ms (40:12,727) | 2363,854 ms (00:02,364)
20 | subquery with equi predicate -> from subquery with group by | dnf | 1467,400 ms (00:01,467)
21 | exists/not exists complex correlated -> left join cte + null check | 498,419 ms | error (explicit join before implicit) | if "select *", will return extra left join columns; much slower than original tpch 21
22 | not exists -> not in | 205,010 ms | 329501,595 ms (05:29,502)
code improvements
smart pointers
throw exceptions

## PSQL Performance
TPCH | original | decorrelated
Q2 | 226,738 ms | 147,444 ms
Q4 | 183,439 ms | 186,085 ms
Q17 | 2412726,898 ms (40:12,727) | 2363,854 ms (00:02,364)
Q20 | dnf | 1467,400 ms (00:01,467)
Q21 | 498,419 ms | error
Q22 | 205,010 ms | 329501,595 ms (05:29,502) | Postgres "not exists" better than "not in" due to null check not in https://explainextended.com/2009/09/16/not-in-vs-not-exists-vs-left-join-is-null-postgresql/

## SQL Parser
Select | from | where | group by | order by | general | questions | answer
column ref | no relation | column ref | column ref | column ref | print RA tree | Figure 8: what is map operator and selection doing?
alias | alias | consts | having |  | (-) column ref
* | cross product | AND/OR/NOT |  |  | like/not like
consts | subqueries | expressions |  |  | views
expressions | left outer join | parenthesis |  |  | substring
rename | correlated subqueries | subqueries |  |  | limit
agg functions (no group by) | using (join) | correlated subqueries |  |  | table schema
| natural (join) | exists (SDJ) |  |  | case expression
|  | not exists (ASDJ) |  |  | expression parenthesis
|  | in (use DJ) |  |  | debug print everything
|  | between |  |  | distinct
|  | date |  |  | extract
|  | interval |  |  | pretty print
|  | all |  |  | print correlated joins
|  | is null/is not null |  |  | tests
TPCH Correlated | missing | TPCH Other | missing | Neumann Q1, Q2 |  | Todos
2 |  | 1 |  | Q1 |  | group by as own operator
4 |  | 3 |  | Q2 |  | order by = sort operator (unter projection)
17 |  | 5 |  |  |  | having operator (like where)
20 |  | 6 |  |  |  | add implicit group by if aggregation func in select
21 |  | 7 |  |  |  | print greek characters
22 |  | 8 |  |  |  | clean up code | relational algebra .cc file
all | detect tpch correlated subquery without alias | 9 |  |  |  |  | proper headers for .h files
|  | 10 |  |  |  |  | initialize Ra Nodes properly
|  | 11 | had problem with group by after unnesting |  |  |  | funcs into classes
|  | 12 |  |  |  |  | deconstructor deletes
|  | 13 |  |  |  | add ' to date cast
|  | 14 |  |  |  | optimize CTEs separately | new RATree class (root, ctes, relation schemas)
|  | 15 |  |  |  | translate in to exists
|  | 16 |  |  |  | translate in list to in subquery
|  | 18 |  |  |  | add null check for in
|  | 19 | "in" in nested boolean |  |  | deparse dependent joins | use left joins by default
change in list to simple predicate
[6 empty] | change where subquery parsing to marker | add markers to subquery (in join), don't deparse markers
add markers to predicate, add test deparse
use semi join for exists, in-join for in
deparse subqueries at predicate markers

## Papers
paper | link | keywords | implements | improves | comment
Optimization of Imperative Programs in a Relational Database | https://arxiv.org/pdf/1712.00498.pdf | optimizing UDFs | no | no
SkinnerDB: Regret-bounded Query Evaluation via Reinforcement Learning | https://dl.acm.org/doi/fullHtml/10.1145/3464389 | reinforcement learning for join ordering | no | no
DuckDB: an Embeddable Analytical Database | https://mytherin.github.io/papers/2019-duckdbdemo.pdf | analytical SQL, embedded OLAP | yes | no
You Say ‘What’, I Hear ‘Where’ and ‘Why’ — (Mis-)Interpreting SQL to Derive Fine-Grained Provenance | https://arxiv.org/pdf/1805.11517.pdf | SQL interpretation, data provenance | no | no
Quantifying TPC-H Choke Points and Their Optimizations | https://www.researchgate.net/profile/Martin-Boissier/publication/341142015_Quantifying_TPC-H_choke_points_and_their_optimizations/links/5ed6b7ab45851529452a3046/Quantifying-TPC-H-choke-points-and-their-optimizations.pdf | TPC-H, choke point optimization | no | no
Optimization of Nested Queries using the NF2 Algebra | http://kops.uni-konstanz.de/bitstream/handle/123456789/33583/Hoelsch_0-326767.pdf?sequence=3&isAllowed=y | NF² algebra, new algebra for optimizing nested queries | no | hmm | Uses NF2 algebra. Only logical optimizations, every logical operator can be mapped to physical operator found in any database system. No new operators introduced
Data dependencies for query optimization: a survey | https://link.springer.com/content/pdf/10.1007/s00778-021-00676-3.pdf | data dependencies | no | no | "Sometimes, correlated subqueries cannot be unnested."
NestGPU: Nested Query Processing on GPU | https://par.nsf.gov/servlets/purl/10227062 | GPU, query unnesting, NestGPU | no | no (GPU specific physical optimization) | "certain nested queries could not be algorithmically unnested"
How How Explains What What Computes — How-Provenance for SQL and Query Compilers | https://www.usenix.org/system/files/conference/tapp2018/tapp2018-paper-ogrady.pdf | SQL how-provenance | no | no
The Art of Balance: A RateupDBTM Experience of Building a CPU/GPU Hybrid Database Product | http://web.cse.ohio-state.edu/hpcs/WWW/HTML/publications/papers/TR-21-4.pdf | CPU/GPU Hybrid DB | no | no (use old method)
Query Lifting Language-integrated query for heterogeneous nested collections | file:///C:/Users/Yannick/Downloads/9783030720193.pdf | heterogeneous query language, set & multiset constructs, "lifting" nested collections | no (similar) | no (new query language) | new query language to unnest queries
Deductive Optimization of Relational Data Storage | https://dl.acm.org/doi/pdf/10.1145/3428238 | Castor: new query language & code compiler, express data layout in query | yes | depends | new query language, in some cases faster than hyper?
Confidentiality and Performance for Cloud Databases | https://www.research-collection.ethz.ch/bitstream/handle/20.500.11850/156247/eth-50668-02.pdf | cloud databases, data confidentiality, encryption | no | no
PgCuckoo: Laying Plan Eggs in PostgreSQL’s Nest | https://db.inf.uni-tuebingen.de/publications/2019/hirn-grust/pgcuckoo-laying-plan-eggs.pdf | insert plan trees into postgreSQL for execution, | yes | no | "adaptation of hyper unnesting strategy"
SQL Comprehension and Synthesis | https://arxiv.org/pdf/2203.03469.pdf | SQL synthesis from natural language | no | no
PgCuckoo — Injecting Physical Plans into PostgreSQL | https://dl.gi.de/bitstream/handle/20.500.12116/21811/D1-8.pdf?sequence=1&isAllowed=y | Inject physical plans into PostgreSQL | no | no | "For PostgreSQL, there is no immediate way to use Neumann and Kemper’s rule system. Ideally, the PostgreSQL developers would integrate this rule system directly with the optimization process of the planner"
Fast Compilation and Execution of SQL Queries with WebAssembly | https://arxiv.org/pdf/2104.15098.pdf | fast query compilation | yes | no | "decorrelation similar to Neumann approach"
A Simplified Architecture for Fast, Adaptive Compilation and Execution of SQL Queries | https://bigdata.uni-saarland.de/publications/Haffner,%20Dittrich%20-%20A%20Simplified%20Architecture%20for%20Fast,%20Adaptive%20Compilation%20and%20Execution%20of%20SQL%20Queries%20@EDBT2023.pdf | JIT Query compilation | no | no
High Performance Iterative Processing in Relational Database Management Systems | https://etd.ohiolink.edu/apexprod/rws_etd/send_file/send?accession=osu1605909940057503&disposition=inline | Improving interative data processing | no | no | "parallel algorithms for nested loop execution of subqueries"

## Parsers
parser | language | SQL dialect | link | license | Github stars | comment
Apache Calcite | Java | Standard SQL | https://github.com/apache/calcite | Apache License v2 | 3.3k
JSQLParser | Java | Oracle, SQLServer, MySQL, PostreSQL | https://github.com/JSQLParser/JSqlParser | Apache License v2 | 3.9k
sqlparse | Python | Generic | https://github.com/andialbrecht/sqlparse | BSD-3-Clause license | 3k | Uses regular expressions
Pingcap | Go | MySQL | https://github.com/pingcap/tidb/tree/master/parser | Apache License v2 | 32k | MySQL parser
SQL Parser | PHP | MySQL | https://github.com/phpmyadmin/sql-parser | GPL-2.0 license | 342
libpg_query | C (wrappers available) | PostgreSQL | https://github.com/pganalyze/libpg_query | BSD-3-Clause license | 728 | Extraced PostgreSQL parser; Wrappers available for Ruby, Go, Javascript, Python, Ocaml, Rust; Used by DuckDB
queryparser | Haskell | Hive, Presto, Vertica | https://github.com/uber/queryparser | Apache License v2 | 1k | Developed by Uber. https://www.uber.com/en-DE/blog/queryparser/
sqlparser-rs | Rust | ANSI/ISO SQL | https://github.com/sqlparser-rs/sqlparser-rs | Apache License v2 | 1.4k
hyrise-sql-parser | C++ |  | https://github.com/hyrise/sql-parser | MIT | 566 | Developed for integration into Hyrise (https://github.com/hyrise/hyrise)
sqlparser | Go | MYSQL | https://github.com/xwb1989/sqlparser | Apache License v2 | 1.1k | From Vitess DB clustering system for MySQL
pgsql-parser | js | PostgreSQL | https://github.com/pyramation/pgsql-parser | MIT | 79 | uses PostgreSQL parser, inbuilt deparser
pg_query | Ruby | PostgreSQL | https://github.com/pganalyze/pg_query | BSD-3-Clause license | 628 | uses PostgreSQL parser, inbuilt deparser
Criteria: |  | Licenses
Long term support |  | Apache License V2 | permissive
License |  | BSD-3-Clause lisence | permissive
Language |  | GPL-2.0 license | copyleft
|  | MIT | permissive

## Optimizers
optmizer | DB/Tool | link | comment | decorrelation Test
EverSQL | multiple DB | https://www.eversql.com/sql-query-optimizer/ | SQL to SQL optimizer Explains optimizations Supports database specific optimizations Not free Wrong output for decorrelation? | Q1 failed
Toad SQL Optimizer for Oracle | Oracle | https://www.quest.com/products/toad-for-oracle/ | "patented re-writing algorithm quickly finds alternative versions of the original SQL statement that will run faster in the database."
SQL Query Tuner |  | https://www.idera.com/productssolutions/sqlserver/sql-query-tuner/ | Suggests SQL rewrites
SQLglot |  | https://github.com/tobymao/sqlglot | SQL optimizer Python | Q1 passed, Q2 failed (traceback error)